## Planning
|  | 5) Committed Stories (100% Velocity) | 0 | 7) Implementation Plan |  |  |  | 0
Planning Assessment Questions
1) Sprint Planning for |  | Story ID | Points | Story # | Description | Points | Task | Est. Hours
Sprint #
Date
Velocity
2) Agreements | Date/Time
Standup
Backlog Refinement
Sprint Review |  | Assessment Questions
Retrospective
Feature Freeze Date |  | 6) Stretch Stories (50% Velocity) | 0
Code Freeze Date |  | Story ID | Points
Agree to Unit Test First
Assessment Questions
3) Definition of Done includes:
0 escaped defects
80% Unit Test Code Coverage
100% Functional Automated Test Coverage |  | Assessment Questions | 97
Assessment Questions
8) Capacity Plan
|  | (max 32 hrs/week) | 0
4) Emergency Procedures: |  | Team Member | Avail Hours
1) If task is taking 2x estimate, try pair programming.
2) If PP doesn't work, swap tasks with another team member.
3) If by Day 3 in sprint and 1 day behind, drop lowest priority story.
4) If PO needs to add story, and story meets DoR, do equitable exchange with other stories in sprint backlog.
5) Abort iteration, notify customer of release plan slip, go immediately into sprint planning.
Assessment Questions
|  | Assessment Questions |  | Assess Qs |  |  |  | 83,84,332

## Review
Review Assessment Questions
1) Sprint Review for
Sprint #
Date
2) Stories Completed |  | 0 |  |  | 5) Next Stories (150% Velocity) |  |  | 0
Story | Desc | Points | Demo (X) | Accepted (X) | Story | Points | Acceptance Crit (X) | Dependencies Cleared (X)
3) New Velocity
4) Updated Release Plan

## Retrospective
Assessment Questions
1) Sprint Retro for | 3) Keep Doing
Sprint #
Date
2) Update Metrics/ Do Assessment
A) Velocity
B) Defect Count | 4) Start Doing
C) Unit Test Code Coverage
D) Functional Automated Test Code Coverage
E) Happiness Metric
Assessment Questions
5) Stop Doing
6) Impediments
| 7) Kaizen Story | 156